## Sheet1
RISK REGISTER FOR BRIGHTLEAF RETAIL (a mid-sized e-Scommerce company, >200 employees)
RISK ID | DATE IDENTIFIED | RISK CATEGORY | RISK OWNER | RISK DESCRIPTION | LIKELIHOOD | IMPACT | RISK SCORE | RISK LEVEL | EXISTING CONTROLS | PLANNED TREATMENT ACTIONS | TARGET DATE | RESIDUAL LIKELIHOOD | RESIDUAL IMPACT | RESIDUAL RISK | RESIDUAL RISK LEVEL | TREAMENT STRATEGY
R-01 | 2026-01-09 | Cybersecurity | Head of IT Security | Unauthorized access to customer payment data due to overly broad employee access permissions. | 3 | 5 | 15 | Critical | Role-based access control on the payment system; quarterly access reviews. | Implement least-privilege access model; MFA on all admin accounts by the end of Q2. | 2026-06-30 | 2 | 5 | 10 | High | Mitigate
R-02 | 2026-01-09 | Cybersecurity/Fraud | CFO | Finance team tricked by a business email compromise (BEC) scam into wiring funds to a fraudulent account. | 4 | 4 | 16 | Critical | None specific to BEC currently in place beyond general email spam filtering. | Introduce mandatory out-of-band phone verification for any payment detail changes; run BEC awareness training for finance staff. | 2026-03-31 | 2 | 4 | 8 | Medium | Mitigate
R-03 | 2026-01-15 | Third-party/Vendor | VP Engineering | Primary payment processor experiences an extended outage, disrupting checkout for all customers | 2 | 4 | 8 | Medium | Single payment processor integration; no automatic failover. | Integrate a secondary backup payment processor for automatic failover. | 2026-09-30 | 2 | 2 | 4 | Low | Mitigate
R-04 | 2026-01-15 | Compliance | Compliance Manager | Failure to meet PCI DSS requirements during the annual compliance audit, risking fines or loss of card processing ability. | 2 | 4 | 8 | Medium | Annual self-assessment questionnaire (SAQ), Network segmentation for cardholder data environment. | Engage a Qualified Security Assessor (QSA) for a pre-audit readiness review. | 2026-05-31 | 1 | 4 | 4 | Low | Mitigate
R-05 | 2026-01-20 | Cybersecurity | Head of IT Security | Customer PII exposed due to an unpatched vulnerability in a third-party e-commerce plugin and may also result in search engine blacklisting and loss of organic search visibility. | 3 | 5 | 15 | Critical | Monthly patch cycle; vulnerability scanning on external-facing systems. | Move to a weekly patch cycle for internet-facing systems; subscribe to vendor security bulletins. | 2026-04-30 | 2 | 5 | 10 | High | Mitigate
R-06 | 2026-01-22 | Operational/HR | VP Engineering | Sole DevOps engineer with no documented succession plan departs, disrupting deployments and infrastructure management | 3 | 3 | 9 | Medium | Basic infrastructure documentation exists but is outdated | Cross-train a second engineer; update infrastructure documentation; consider a managed DevOps contractor as backup. | 2026-08-31 | 2 | 2 | 4 | Low | Mitigate
R-07 | 2026-01-25 | Operational | Head of Operations | Single-source overseas supplier experiences a shipping delay, causing stockouts on best-selling products | 3 | 3 | 9 | Medium | Standard purchase order lead times; no alternate supplier identified. | Qualify a second supplier in a different region for top 10 SKUs. | 2026-07-31 | 2 | 2 | 4 | Low | Mitigate
R-08 | 2026-01-25 | Reputational | Head of Marketing/Comms | Public backlash and customer trust loss following disclosure of any future data breach | 2 | 4 | 8 | Medium | Draft incident communication template exists but has not been tested. | Run a tabletop exercise simulating a breach disclosure; finalize the incident communication plan. | 2026-06-30 | 2 | 3 | 6 | Low | Mitigate
R-09 | 2026-01-28 | Financial | CFO | Currency exchange rate fluctuation increases the cost of imported inventory, compressing margins | 3 | 2 | 6 | Medium | Informal monitoring of exchange rates by finance team. | Continue monitoring; revisit if rate volatility exceeds 10% in a quarter. | 2026-12-31 | 3 | 2 | 6 | Low | Accept
R-10 | 2026-01-28 | HR/Cybersecurity | Head of IT Security | Employees fall for social engineering (phishing, pretexting) due to limited security awareness training | 4 | 3 | 12 | High | One-time security awareness training during the onboarding of new staff. | Launch quarterly phishing simulations and refresher training for all staff. | 2026-05-31 | 2 | 3 | 6 | Low | Mitigate
R-11 | 2026-01-28 | Cybersecurity /Operational Availability | VP Engineering | A distributed denial-of-service (DDoS) attack overwhelms Brightleaf's website or checkout infrastructure, causing extended downtime and lost sales during the attack window | 3 | 4 | 12 | High | Standard cloud hosting firewall; no dedicated DDoS mitigation service or CDN-based traffic filtering currently in place. | Implement a DDoS mitigation/CDN service (e.g., Cloudflare, AWS Shield); set up real-time traffic monitoring and auto-scaling; build a DDoS-specific incident response runbook. | 2026-11-20 | 2 | 2 | 4 | Low | Mitigate

## Sheet2
RISK MATRIX REFERENCE
| 1 | 2 | 3 | 4 | 5
1 | 1 | 2 | 3 | 4 | 5
2 | 2 | 4 | 6 | 8 | 10
3 | 3 | 6 | 9 | 12 | 15
4 | 4 | 8 | 12 | 16 | 20
5 | 5 | 10 | 15 | 20 | 25
LIKELIHOOD SCALE (how likely is this to happen?)
Score | Rating | Description
1 | Rare | Could happen, but there's been no known instance in the industry or in Brightleaf
2 | Unlikely | Could happen once every few years
3 | Possible | Could happen at some point this year
4 | Likely | Expected to happen more than once this year
5 | Almost Certain | Expected to happen repeatedly
IMPACT SCALE (how bad would it be if this occurred?)
Score | Rating | Description
1 | Negligible | Under $10k impact, no downtime, no data or customer impact
2 | Minor | $10k-$50k impact, brief internal disruption, no customer-facing effect
3 | Moderate | $50k-$250k impact, noticeable downtime or a small number of customers affected
4 | Major | $250k-$1M impact, significant downtime, regulatory attention , or a data exposure affecting many customers
5 | Severe | Over $1Mimpact, large-scale data breach, major regulatory/legal action, or threat to business continuity
RISK LEVEL BANDS (i.e RISK SCORE= Likelihood x Impact, range 1-25
Score Range | Level | Suggested Response to Risk
1-4 | Low | Monitor, Accept or address at routine review.
5-9 | Medium | Assign an owner and a risk treatment plan within a normal planning cycle.
10-14 | High | Prioritize treatment. Report to management.
15-25 | Critical | Immediate action required. Escalate to leadership/ board of Directors